Shattered Realms Immersive Website

Development Plan

Agile / Scrum - Sprint Planning, Backlog & Roadmap

Agile / Scrum Framework	1

Roles	2

Definition of Ready	2

Definition of Done	2

Story Points & Estimation	3

Product Backlog	3

Epic Overview	3

Prioritised Product Backlog	4

Sprint Roadmap	6

Tools & Workflow	7

Recommended Tools	7

Git Branching Strategy	7

Sprint Board Columns	7

# Agile / Scrum Framework

With two developers, the Scrum process will be lightweight. Ceremony overhead will be minimal

| Ceremony | Recommendation |
| --- | --- |
| Sprint Length | 2 weeks - short enough to stay focused, long enough to complete meaningful work. |
| Sprint Planning | 1–2 hours at the start of each sprint. Review the backlog, agree on sprint goal, select and assign stories. |
| Daily Standup | 10-15 minutes. Async (Discord / messaging) is fine, calls preferred Cover: done yesterday, doing today, any blockers. |
| Sprint Review | 30-60 minutes. Demo working features. |
| Retrospective | 30 minutes. What went well, what didn't, one thing to change next sprint. |
| Backlog Refinement | 30-60 minutes mid-sprint. Review upcoming stories, add detail, estimate, and re-prioritise. |

## Roles

- Lead Developer - Acts as both developer and de facto Scrum Master.

Owns the backlog, prioritises work, removes blockers for the developers, and ensures the sprint goal is met.

- Developer - Full team member. Takes on stories appropriate to their skill level. Responsible for their own work, attending ceremonies, and raising blockers promptly.

- Product Owner - Ideally a society representative or stakeholder who can validate that built features meet real needs.

If no dedicated PO, the lead developer holds this responsibility.

## Definition of Ready

A story is ready to be worked on in a sprint when:

- It has a clear title and description.

- Acceptance criteria are defined (what must be true for the story to be 'done').

- It has been estimated (story points).

- Any dependencies are identified and resolved.

## Definition of Done

A story is done when:

- The feature is built and works as described in the acceptance criteria.

- Unit/integration tests are written and passing.

- The code has been reviewed (even informally by lead to developer or vice versa).

- Relevant documentation is updated (API docs, Overview if needed).

- The feature is merged to master and does not break the build.

# Story Points & Estimation

Use the Fibonacci-inspired scale: 1, 2, 3, 5, 8, 13.

Points represent relative effort and complexity, not hours.

As a guide:

| Points | What it typically means |
| --- | --- |
| 1 | Trivial change. A config tweak, a copy change, a very simple UI element. |
| 2 | Small, well-understood task. A simple CRUD endpoint or basic Blazor component. |
| 3 | Standard feature. A typical user story with some logic - e.g. character creation form. |
| 5 | Medium complexity. Multiple layers involved, some non-trivial logic or integration. |
| 8 | Complex story. Significant effort, likely touching domain, application and presentation layers. |
| 13 | Very large - should be split if possible. Indicates uncertainty or high complexity. |

# Product Backlog

The backlog is ordered by priority:

- Must Have (core, non-negotiable),

- Should Have (important but not blocking launch),

- Could Have (nice to have).

## Epic Overview

| # | Epic | Description |
| --- | --- | --- |
| E1 | Authentication & Accounts | User registration, login, profile management, roles. |
| E2 | Character Management | Create, view characters; EM assigns XP and level. |
| E3 | Wiki | View, create, edit wiki entries by category. |
| E4 | Forum | Categories, threads, posts, moderation. |
| E5 | Homepage | Announcements, links, role-based content visibility. |
| E6 | Video Hosting | Upload, approve, stream videos with size restrictions. |
| E7 | Reporting & Analytics | Event, forum, wiki, and user reports for Admin/Analyst. |
| E8 | Audit Logging | Activity log, admin read access, System-only edit/delete. |
| E9 | Admin & Moderation | User management, content moderation, system settings. |
| E10 | GDPR & Compliance | Data export, right to erasure, privacy controls. |

## Prioritised Product Backlog

| ID | Epic | Story | Priority | Estimate |
| --- | --- | --- | --- | --- |
| 001 | E1 | As a new user, I want to register an account with my email and a password so I can access the site. | Must Have |  |
| 002 | E1 | As a registered user, I want to log in securely so I can access my account. | Must Have |  |
| 003 | E1 | As a user, I want to update my profile including contact information and emergency contact details. | Must Have |  |
| 004 | E1 | As an admin, I want to assign or change a user's role (User, EventManager, Analyst, Admin). | Must Have |  |
| 005 | E2 | As a user, I want to create a new character with a name and nationality. | Must Have |  |
| 006 | E2 | As a user, I want to view my own characters and their level and experience. | Must Have |  |
| 007 | E2 | As an Event Manager, I want to assign experience points to a character. | Must Have |  |
| 008 | E2 | As an Event Manager, I want to set a character's level. | Must Have |  |
| 009 | E2 | As an Event Manager, I want to view characters belonging to any user. | Must Have |  |
| 010 | E3 | As a user, I want to browse wiki entries by category. | Must Have |  |
| 011 | E3 | As a user, I want to read a full wiki entry. | Must Have |  |
| 012 | E3 | As an Event Manager, I want to create a new wiki entry. | Must Have |  |
| 013 | E3 | As an Event Manager, I want to edit an existing wiki entry. | Must Have |  |
| 014 | E4 | As a user, I want to browse forum categories. | Must Have |  |
| 015 | E4 | As a user, I want to view threads within a category. | Must Have |  |
| 016 | E4 | As a user, I want to create a new thread in a category. | Must Have |  |
| 017 | E4 | As a user, I want to reply to an existing thread. | Must Have |  |
| 018 | E4 | As a user, I want to edit or delete my own posts. | Must Have |  |
| 019 | E4 | As an Event Manager, I want to pin or lock threads as a moderator. | Must Have |  |
| 020 | E4 | As an Event Manager, I want to delete any post or thread as a moderator. | Must Have |  |
| 021 | E5 | As a user, I want to see a homepage with announcements relevant to my role. | Must Have |  |
| 022 | E5 | As an Event Manager, I want to create and edit homepage announcements. | Must Have |  |
| 023 | E6 | As an Event Manager, I want to upload a video with a title and description. | Should Have |  |
| 024 | E6 | As an Event Manager, I want to approve or reject a pending video upload. | Should Have |  |
| 025 | E6 | As a user, I want to watch approved videos on the site. | Should Have |  |
| 026 | E7 | As an Admin, I want to view a report of user registration and activity stats. | Should Have |  |
| 027 | E7 | As an Analyst, I want to view forum usage statistics. | Should Have |  |
| 028 | E7 | As an Analyst, I want to view wiki page views and edit history stats. | Should Have |  |
| 029 | E8 | As a system, every significant user action is recorded in the activity log. | Must Have |  |
| 030 | E8 | As an Admin, I want to view and filter the activity log. | Must Have |  |
| 031 | E9 | As an Admin, I want to deactivate or delete a user account. | Must Have |  |
| 032 | E9 | As an Admin, I want to create and manage forum categories. | Should Have |  |
| 033 | E10 | As a user, I want to export my personal data in a readable format. | Should Have |  |
| 034 | E10 | As an Admin, I want to process a right-to-erasure request for a user. | Should Have |  |
| 035 | E6 | As a user, I want to see a list of upcoming events on the homepage. | Could Have |  |
| 036 | E4 | As a user, I want to search the forum by keyword. | Could Have |  |
| 037 | E3 | As a user, I want to search the wiki by keyword. | Could Have |  |
| 038 | E7 | As an Analyst, I want to export reports as a CSV file. | Could Have |  |

# Sprint Roadmap

This is a suggested roadmap based on logical dependencies and priority.

Each sprint is 2 weeks.

Adjustments may be made based on actual team velocity.

| Sprint | Theme | Stories | Goal |
| --- | --- | --- | --- |
| 1 | Foundation | 001, 002, 003, 004 | Users can register, log in, manage their profile and have roles assigned. The core identity layer is in place. |
| 2 | Characters | 005, 006, 007, 008, 009 | Characters can be created and viewed by users. Event Managers can assign XP and level. |
| 3 | Wiki | 010, 011, 012, 013, 029, 030 | The wiki is readable by all users. Event Managers can create and edit entries. Audit logging is active. |
| 4 | Forum Basics | 014, 015, 016, 017, 018 | Users can browse categories, create threads, and post replies. Users can manage their own content. |
| 5 | Forum Moderation & Homepage | 019, 020, 021, 022 | Event Managers can moderate the forum. A role-aware homepage is live. |
| 6 | Admin & GDPR | 031, 032, 033, 034 | Admins can manage users. Data export and erasure flows meet GDPR requirements. |
| 7 | Video Hosting | 023, 024, 025 | Event Managers can upload and approve videos. Users can watch approved content. |
| 8 | Reporting | 026, 027, 028 | Admins and Analysts can view reporting dashboards. |
| 9+ | Enhancement | 035, 036, 037, 038 | Search, event listings, CSV export, and other Could Have features. |

Note: Story 029 (activity logging) is introduced in Sprint 3 but should be built as infrastructure that can be called from any layer. Incrementally extend it as new features are added in subsequent sprints.

# Tools & Workflow

## Recommended Tools

| Purpose | Tool / Recommendation |
| --- | --- |
| Backlog & Sprint Board | GitHub Projects |
| Version Control | Git with GitHub |
| Branching Strategy | GitHub Flow: one master branch, short-lived feature branches, pull requests with review before merge. |
| Commit Convention | Conventional Commits: feat:, fix:, docs:, test:, refactor:, chore: |
| CI/CD | GitHub Actions - automate build, test, and deployment. |
| Communication | Discord for async daily standups and quick questions. |
| Design / Wireframes | Figma (free tier) or Balsamiq for low-fi wireframes before building UI. |

## Git Branching Strategy

- master - always deployable. Protected branch. No direct commits.

- feature/story-id-short-description - created from main for each story (e.g. feature/005-character-creation).

- fix/short-description - for bug fixes outside of a story.

- All merges to main go through a Pull Request.

## Sprint Board Columns

- Backlog - stories not yet in a sprint.

- To Do - stories selected for the current sprint, not yet started.

- In Progress - actively being worked on.

- In Review - code complete, pull request open.

- Done - merged, tested, meets Definition of Done.

Shattered Realms Immersive Website - Development Plan - Agile/Scrum